Contract Data:

Engineering and Construction Short Contract

Engineering and Construction

Short Contract

| A contract between | Westcountry Rivers Trust Rain Charm House, Kyl Kober Parc, Stoke Climsland, Cornwall, PL17 8PH |
| --- | --- |

| and |  |
| --- | --- |

| for | Natural Flood Management interventions of leaky dams, flow spreaders, peat bunds and scrapes on Clinton Devon Estate’s Pebblebed Heaths Bicton Mire |
| --- | --- |

Contract Forms

Contract Data

The Contractor’s Offer and Client’s Acceptance

Price List

Scope

Site Information

Notes about the contract are printed in boxes like this one. They are not part of the contract.

Contract Data

The Client’s Contract Data

The Client is

| Name | Westcountry Rivers Trust |
| --- | --- |
| Address for communications | Rain Charm House, Kyl Cober Parc, Stoke Climsland, Cornwall, PL17 8PH |

| Address for electronic communications | millybowden@wrt.org.uk |
| --- | --- |

| The works are | Natural Flood Management interventions of leaky dams, flow spreaders, peat bunds and scrapes on Clinton Devon Estate’s Pebblebed Heaths Bicton Mire |
| --- | --- |

| The site is | Pebblebed Heaths, Clinton Devon Estates |
| --- | --- |

| The starting date is | 13th February 2026 |
| --- | --- |

| The completion date is | 13th March 2026 unless by prior agreement |
| --- | --- |

| The delay damages are | £50 | per day |
| --- | --- | --- |

| The period for reply is | One | weeks |
| --- | --- | --- |

| The defects date is | Four | weeks after Completion |
| --- | --- | --- |

| The defect correction period is | Eight | weeks |
| --- | --- | --- |

| The assessment day is the | Last Thursday | of each month |
| --- | --- | --- |

| The retention is | 5 | % |
| --- | --- | --- |

The United Kingdom Housing Grants, Construction and Regeneration Act (1996) does/does not apply

(delete as applicable)

The Adjudicator is

| Name | Construction Industry Council (CIC) |
| --- | --- |

| Address for communications | Construction Industry Council (CIC) The Building Centre 26 Store Street London WC1E 7BT |
| --- | --- |

| Address for electronic communications | enquiries@cic.org.uk |
| --- | --- |

Contract Data

The Client’s Contract Data

| The interest rate on late payment is | 0.15 | % per complete week of delay. |
| --- | --- | --- |

Insert a rate only if a rate less than 0.5% per week of delay has been agreed.

| For any one event, the liability |  |
| --- | --- |
| of the Contractor to the Client |  |
| for loss of or damage to the |  |
| Client’s property is limited to | 5,000,000 |

| The Client provides this insurance | None |
| --- | --- |

Only enter details here if the Client is to provide insurance.

| The minimum amount of |  |
| --- | --- |
| cover for the third insurance |  |
| stated in the Insurance Table is, |  |
| for any one event | 5,000,000 |

| The minimum amount of |  |
| --- | --- |
| cover for the fourth insurance |  |
| stated in the Insurance Table |  |
| is, for any one event | 5,000,000 |

| The Adjudicator nominating |  |
| --- | --- |
| body is | Construction Industry Council (CIC) |

| The tribunal is | Arbitration |
| --- | --- |

| If the tribunal is arbitration, the |  |
| --- | --- |
| arbitration procedure is | The latest version of the Institution of Civil Engineers Arbitration Procedure in force when arbitrator is appointed |

The conditions of contract are the NEC4 Engineering and Construction Short Contract June 2017 (with amendments October 2020) and the following additional conditions

Only enter details here if additional conditions are required.

None

Contract Data

The Contractor’s Contract Data

The Contractor is

| Name | To be completed by the contractor |
| --- | --- |
| Address for communications |  |

| Address for electronic communications |  |
| --- | --- |

| The fee percentage is |  | % |
| --- | --- | --- |

The people rates are

| category of person | unit | rate |
| --- | --- | --- |

| The published list of Equipment is |  |
| --- | --- |

| The percentage for adjustment for Equipment is |  | % (state plus |
| --- | --- | --- |
|  |  | or minus) |

The Contractor’s Offer and Client’s Acceptance

The Contractor offers to Provide the Works in accordance with these conditions of contract for an amount to be determined in accordance with these conditions of contract.

| The offered total of the Prices is |  |
| --- | --- |

Enter the total of the Prices from the Price List.

Signed on behalf of the Contractor

| Name |  |
| --- | --- |

| Position |  |
| --- | --- |

| Signature |  |
| --- | --- |

| Date |  |
| --- | --- |

The Client accepts the Contractor’s Offer to Provide the Works

Signed on behalf of the Client

| Name |  |
| --- | --- |

| Position |  |
| --- | --- |

| Signature |  |
| --- | --- |

| Date |  |
| --- | --- |

Price List

Entries in the first four columns in this Price List are made either by the Client or the tenderer. If the Contractor is to be paid an amount for the item which is not adjusted if the quantity of work in the item changes, the tenderer enters the amount in the Price column only; the Unit, Quantity and Rate columns being left blank. If the Contractor is to be paid an amount for the item of work which is the rate for the work multiplied by the quantity completed, the tenderer enters the rate which is then multiplied by the expected quantity to produce the Price, which is also entered.

| ITEM NUMBER | DESCRIPTION | UNIT | QUANTITY | RATE | PRICE |
| --- | --- | --- | --- | --- | --- |

| The total of the Prices | TBC |
| --- | --- |

The method and rules used to compile the Price List are

Scope

The Scope should be a complete and precise statement of the Client’s requirements. If it is incomplete or imprecise there is a risk that the Contractor will interpret it differently from the Client’s intention. Information provided by the Contractor should be listed in the Scope only if the Client is satisfied that it is required, is part of a complete statement of the Client’s requirements and is consistent with the other parts of the Scope.

1 Description of the works

Give a detailed description of what the Contractor is required to do and of any work the Contractor is to design.

Services Required: A series of 23 wool/woody logs and shallow peat bunds are to be constructed along the northern tributary. Installing leaky dams will hold back the highest flows so will slow the flow of water and the displacement of sediment and bed material. Creation of 4 shallow scrapes will capture overland flows and ephemeral streams to hold back water giving it time to infiltrate into the surrounding landscape. - An option of Ground Investigations according to the Consultant’s assessment and agreement with the Client as to whether they are needed. - Appropriate risk assessments will be required for all elements of the services. Under CDM 2015 this includes a Designers Risk Assessment (DRA). - Optioneering for the above outcomes is welcomed against your experience. WRT have provided a Concept Plan, based on technical input, however, WRT are not technical design experts, and while operating as Principal Designer under CDM regulations WRT expect the appointed designer to provide comment on feasibility, health and safety, and budget practicality of options based on your technical experience. - The consultant must ensure that all elements conform to all relevant British and European Standards. - A draft NEC4 Contract representative of the final version has been supplied. A final version will be provided at appointment, with opportunity to review before acceptance. Concept Plan: Wool/woody logs - Fleece from sheep can be used in different ways to slow water flows, capture sediment, and disrupt erosional energy. The wool can be made into logs or stuffed into dams which are then secured in place to provide a permeable barrier that will raise water levels using natural materials. The fleeces will provide a more sustainable alternative to coir rolls or matting and can be processed in the UK without synthetic materials or importing coir. - Within the valley basin, flow spreader logs on woody dams can be used. - The size, design and construction techniques for leaky dams are site specific. Works will be carried out by a trusted contractor. General design principles for woody log dams are as follows (this will be adapted for wool logs): - Carefully selected trees along the watercourse will be felled to provide the materials for constructing the leaky dams. This material will likely need to be selected from adjacent Clinton Devon plantation woodlands. - The leaky dam should be 2 times the width of the channel. - Construct the dam from logs large enough to span the water channel and out on to the floodplain to provide a stable and long-lasting structure. - Align dams at right angles to channel banks to reduce bank scour. - Build dams to allow low flows and fish to always pass unimpeded at all times. - Site dams on slow flowing reaches of the watercourse. - Build dams to a height sufficient to encourage water to spread onto the floodplain upstream of the dam or hold water within the channel itself. Note it is not advised to build the dam higher than approximately 0.5 m. - Steel pins can be used to secure the structure to the ground and create to a large mass of logs which is unlikely to move during high flows. - Build dams in series (minimum 3 dams) at a spacing between dams of about 5-7 times the width of the channel. - Make sure dams are not installed directly upstream of pinch points such as bridges or culverts that back up flows and are likely to swamp the dam. Dams should be no closer than 20m from culverts in offline ditches and at least 30m away in the river channel. Peat bunds The size, design and construction techniques for peat bunds are site specific. Works will be carried out by a trusted contractor. General design principles are: - Carefully remove the surface vegetation (turves) in strips and set them aside to be used for capping - Excavate degraded peat - Use the good, wet peat excavated to construct a bund - Thoroughly compact this peat layer, building it up to create a solid, watertight barrier up to 300mm height - Place the reserved surface vegetation (turves) back on top of the compacted peat, butting them together to prevent erosion. - Compact the turves firmly onto the bund. - Backfill any borrow pits with degraded peat, reprofile the area to a gentle slope, and replace the turf or vegetation to minimise bare peat. Scrapes The next step beyond wool logs, dams & flow spreaders would be to create habitat on the adjoining land to the bank which will hold water when the water is overtopped from the channel by these interventions. This would be through the creation of scrapes – shallow irregular shaped depressions in the land surface that will receive water from the flow spreaders. The size, design and construction techniques for scrapes are site specific. Works will be carried out by a trusted contractor. General design principles are: - Vegetation Clearance: Cut back existing vegetation in the selected area and establish a margin of short vegetation (at least 10m wide) around the planned scrape. - Excavation: Use low impact earthmoving equipment, such as tracked excavators, to remove the soil in the designated area. Excavate to a maximum depth of 750 – 900mm, with variations in depth and multiple sumps being beneficial. The edges should be gently sloping to create a wide "drawdown zone" of damp, muddy shoreline as water levels fall. - Outlet: a lower level for water to drain from should be created with a brashy dam and bed to reduce scour of the outfall. - Finish: Leave the base of the scrape with a rough, lumpy finish (not smoothly graded like a garden pond) to add micro-variations in habitat. - Spoil Disposal: The excavated peat can be used in the bund creation (above) this bund should be included in the total scrape depth. For further information, please refer to the Invitation to Tender.

2 Drawings

List the drawings that apply to the contract.

| DRAWING NUMBER | REVISION | TITLE |
| --- | --- | --- |
| 1 |  | Invitation to Tender – Appendix A |

Scope

3 Specifications

List the specifications which apply to the contract.

| TITLE | DATE OR REVISION | TICK IF PUBLICLY AVAILABLE |
| --- | --- | --- |
| Invitation to Tender | 1 |  |

4 Constraints on how the Contractor Provides the Works

State any constraints on the sequence and timing of work and on the methods and conduct of work including the requirements for any work by the Client.

All works are subject to the NE SSSI Consent and DCC Land Drainage Consent approval. Communications - While the Client is Westcountry Rivers Trust, the site is in the Clinton Devon Estates ownership and management. Communications will need to involve the Westcountry Rivers Trust project manager as well as Pebblebed Heaths Manager Kim Strawbridge. Site access specifically will need to be coordinated with Clinton Devon Estates, the landowner. Health and Safety - The Pebblebed Heaths is open access land with Military of Defence, forestry and conservation operations also occurring. All gates should be opened and closed immediately behind to limit vehicular access. - Access should be discussed with Kim Strawbridge of the Pebblebed Heaths Conservation Trust and Clinton Devon Estates - Ground conditions may change and disturbance should be kept to a minimum-do NOT stray other than in the project area. The tracks are in a protected habitat and designated SSSI. Works must be completed by the 13th March as best you can to avoid bird nesting season unless by prior agreement. Where the Consultant intends to subcontract part of the works, this should be agreed with the Client in advance. The Consultant should ensure that Health & Safety due diligence is carried out and provided to the Client in respect of the Subcontractor either in the form of the WRT Health & Safety Assessment Form or equivalent. As per Condition 21 of the Contract, if the Consultant subcontracts work, it is responsible for Providing the Service as if it had not been subcontracted. Where a Subcontractor is used, The Client reserves the right to instruct the Consultant to stop using a person to Provide the Service. Any disputes are to be resolved in the first instance by the Project Managers of the Client and Consultant. Where a resolution between these two designated individuals is not possible, the dispute should be escalated to the Chief Executives of the parties for resolution. Should the Chief Executives fail to reach agreement the dispute is to be referred to a neutral third party for mediation / conciliation. Only when these steps fail should the dispute be resolved in line with the Contract Data as set out on page 4 of this contract

Scope

5 Requirements for the programme

State whether a programme is required and, if it is, state what form it is to be in, what information is to be shown on it, when it is to be submitted and when it is to be updated. State what the use of the works is intended to be at their Completion as defined in clause 11.2(1).

All works are subject to the NE SSSI Consent and DCC Land Drainage Consent approval. Works must be completed by the 13th March 2026 to avoid bird nesting season -TBC by Natural England SSSI consent. Monthly meetings to be held between the client and the contractor.

6 Services and other things provided by the Client

Describe what the Client will provide, such as services (including water and electricity) and ‘‘free issue’’ Plant and Materials and equipment.

| ITEM | DATE BY WHICH IT WILL BE PROVIDED |
| --- | --- |

Site Information

Give information about the site such as the ground conditions and any other information which is likely to affect the Contractor’s work such as the position of adjacent structures.

The site is located on the Pebblebed Heaths, Clinton Devon Estate. - The land is in the East Devon AONB and is in the Pebblebed Heaths SSSI. SSSI consent is required before works commenced, this has been requested but as of 12/1/26 not been approved. - The landowner is Clinton Devon Estates. - This site has designated status and any concerns or queries should be directed to Milly Bowden and the Pebblebed Heaths manager Kim Strawbridge. - The heath is used by rangers, forestry, MOD and the general public. - The site has public access and controlled grazing, in addition to use under a historic agreement by the Royal Marines as a training ground for recruits. - The Royal Marines use an encampment within the common and an endurance course where groups of recruits run around the route across the common. This has caused damage and degradation to the fen, bog, and heath habitats, in addition to exacerbated erosion of peatland soils. Bicton Mire: Grid reference SY 03975 85933 Google maps public car park locations for Pebblebed Heaths access with yellow lines as access tracks: Bicton Common: https://maps.app.goo.gl/NquCPW4d5w1uLGCE6

23 Wool logs and shallow peat bunds

4 Shallow scrapes with gentle undulating edges

Items in the orange text boxes are to be completed in this phase.