Contract Data:

Engineering and Construction Short Contract

Engineering and Construction

Short Contract

| A contract between | Westcountry Rivers Trust Rain Charm House, Kyl Kober Parc, Stoke Climsland, Cornwall, PL17 8PH |
| --- | --- |

| and |  |
| --- | --- |

| for | Natural Flood Management interventions of leaky dams, a swale and cross drains in an area called Islands on Clinton Devon Estate’s Pebblebed Heaths and forestry land. |
| --- | --- |

Contract Forms

Contract Data

The Contractor’s Offer and Client’s Acceptance

Price List

Scope

Site Information

Notes about the contract are printed in boxes like this one. They are not part of the contract.

Contract Data

The Client’s Contract Data

The Client is

| Name | Westcountry Rivers Trust |
| --- | --- |
| Address for communications | Rain Charm House, Kyl Cober Parc, Stoke Climsland, Cornwall, PL17 8PH |

| Address for electronic communications | millybowden@wrt.org.uk |
| --- | --- |

| The works are | Natural Flood Management interventions of leaky dams, a swale and cross drains in an area called Islands on Clinton Devon Estate’s Pebblebed Heaths and forestry land. |
| --- | --- |

| The site is | Islands, Pebblebed Heaths, Clinton Devon Estates |
| --- | --- |

| The starting date is | 1st September 2026 |
| --- | --- |

| The completion date is | 30th September 2026 |
| --- | --- |

| The delay damages are | £50 | per day |
| --- | --- | --- |

| The period for reply is | One | weeks |
| --- | --- | --- |

| The defects date is | Four | weeks after Completion |
| --- | --- | --- |

| The defect correction period is | Eight | weeks |
| --- | --- | --- |

| The assessment day is the | Last Thursday | of each month |
| --- | --- | --- |

| The retention is | 5 | % |
| --- | --- | --- |

The United Kingdom Housing Grants, Construction and Regeneration Act (1996) does/does not apply

(delete as applicable)

The Adjudicator is

| Name | Construction Industry Council (CIC) |
| --- | --- |

| Address for communications | Construction Industry Council (CIC) The Building Centre 26 Store Street London WC1E 7BT |
| --- | --- |

| Address for electronic communications | enquiries@cic.org.uk |
| --- | --- |

Contract Data

The Client’s Contract Data

| The interest rate on late payment is | 0.15 | % per complete week of delay. |
| --- | --- | --- |

Insert a rate only if a rate less than 0.5% per week of delay has been agreed.

| For any one event, the liability |  |
| --- | --- |
| of the Contractor to the Client |  |
| for loss of or damage to the |  |
| Client’s property is limited to | 5,000,000 |

| The Client provides this insurance | None |
| --- | --- |

Only enter details here if the Client is to provide insurance.

| The minimum amount of |  |
| --- | --- |
| cover for the third insurance |  |
| stated in the Insurance Table is, |  |
| for any one event | 5,000,000 |

| The minimum amount of |  |
| --- | --- |
| cover for the fourth insurance |  |
| stated in the Insurance Table |  |
| is, for any one event | 5,000,000 |

| The Adjudicator nominating |  |
| --- | --- |
| body is | Construction Industry Council (CIC) |

| The tribunal is | Arbitration |
| --- | --- |

| If the tribunal is arbitration, the |  |
| --- | --- |
| arbitration procedure is | The latest version of the Institution of Civil Engineers Arbitration Procedure in force when arbitrator is appointed |

The conditions of contract are the NEC4 Engineering and Construction Short Contract June 2017 (with amendments October 2020) and the following additional conditions

Only enter details here if additional conditions are required.

None

Contract Data

The Contractor’s Contract Data

The Contractor is

| Name | To be completed by the contractor |
| --- | --- |
| Address for communications |  |

| Address for electronic communications |  |
| --- | --- |

| The fee percentage is |  | % |
| --- | --- | --- |

The people rates are

| category of person | unit | rate |
| --- | --- | --- |

| The published list of Equipment is |  |
| --- | --- |

| The percentage for adjustment for Equipment is |  | % (state plus |
| --- | --- | --- |
|  |  | or minus) |

The Contractor’s Offer and Client’s Acceptance

The Contractor offers to Provide the Works in accordance with these conditions of contract for an amount to be determined in accordance with these conditions of contract.

| The offered total of the Prices is |  |
| --- | --- |

Enter the total of the Prices from the Price List.

Signed on behalf of the Contractor

| Name |  |
| --- | --- |

| Position |  |
| --- | --- |

| Signature |  |
| --- | --- |

| Date |  |
| --- | --- |

The Client accepts the Contractor’s Offer to Provide the Works

Signed on behalf of the Client

| Name |  |
| --- | --- |

| Position |  |
| --- | --- |

| Signature |  |
| --- | --- |

| Date |  |
| --- | --- |

Price List

Entries in the first four columns in this Price List are made either by the Client or the tenderer. If the Contractor is to be paid an amount for the item which is not adjusted if the quantity of work in the item changes, the tenderer enters the amount in the Price column only; the Unit, Quantity and Rate columns being left blank. If the Contractor is to be paid an amount for the item of work which is the rate for the work multiplied by the quantity completed, the tenderer enters the rate which is then multiplied by the expected quantity to produce the Price, which is also entered.

| ITEM NUMBER | DESCRIPTION | UNIT | QUANTITY | RATE | PRICE |
| --- | --- | --- | --- | --- | --- |

| The total of the Prices | TBC |
| --- | --- |

The method and rules used to compile the Price List are

Scope

The Scope should be a complete and precise statement of the Client’s requirements. If it is incomplete or imprecise there is a risk that the Contractor will interpret it differently from the Client’s intention. Information provided by the Contractor should be listed in the Scope only if the Client is satisfied that it is required, is part of a complete statement of the Client’s requirements and is consistent with the other parts of the Scope.

1 Description of the works

Give a detailed description of what the Contractor is required to do and of any work the Contractor is to design.

Services Required: - A cascade of up to 12 leaky woody dams will be placed in the Budleigh Brook flowing through the deciduous woodland (as approved with the MOD) on the eastern side of the Bicton Common area of the Pebblebed Heaths SSSI with a further 12 in the tributary flowing into the channel from the south. Flow spreaders will be placed on overland flow pathways to supplement these in channel dams. - The stream then enters Islands Plantation woodland owned and managed by Clinton Devon Estates. A cascade of up to 15 dams will be placed in this section of stream. - Two sleeping policemen cross drains where the track is scouring on the bend will divert water into the plantation woodland. - A long (75m) cross slope blind ditch or swale will be dug into the open ground and naturally regenerated sub compartment which will be at a tangent to the slope of the hill to intercept flow pathways - An option of Ground Investigations according to the Consultant’s assessment and agreement with the Client as to whether they are needed. - Appropriate risk assessments will be required for all elements of the services. Under CDM 2015 this includes a Designers Risk Assessment (DRA). - Optioneering for the above outcomes is welcomed against your experience. WRT have provided a Concept Plan, based on technical input, however, WRT are not technical design experts, and while operating as Principal Designer under CDM regulations WRT expect the appointed designer to provide comment on feasibility, health and safety, and budget practicality of options based on your technical experience. - The consultant must ensure that all elements conform to all relevant British and European Standards. Concept Plan Leaky dams will slow the movement of water and will increase temporary storage of flood waters within water channels and out on to the floodplain, help delay the passage of flood water downstream, allow sediment to settle out and reduce downstream flood risk. A Swale collects surface runoff water from land, allowing sediment to settle to the bottom and water to enter the ground. This helps to reduce runoff and the risk of soil erosion. Swales will slow water flows during heavy rainfall and reduce downstream flooding and support water resources. Cross drains divert overland track flow from a near impermeable surface into heathland or ground which can absorb water. For further information and proposed construction methods, please refer to the Invitation to Tender.

2 Drawings

List the drawings that apply to the contract.

| DRAWING NUMBER | REVISION | TITLE |
| --- | --- | --- |
| 1 |  | Invitation to Tender – Appendix A |

Scope

3 Specifications

List the specifications which apply to the contract.

| TITLE | DATE OR REVISION | TICK IF PUBLICLY AVAILABLE |
| --- | --- | --- |
| Invitation to Tender | 12th June 2026 |  |

4 Constraints on how the Contractor Provides the Works

State any constraints on the sequence and timing of work and on the methods and conduct of work including the requirements for any work by the Client.

All works are subject to the conditions of the NE SSSI Consent and DCC Land Drainage Consent as detailed in the Scope and in the ITT. No deviation is permitted without prior discussion. Copies of the NE SSSI Consent and Land Drainage Consent can be provided if required. Communications - While the Client is Westcountry Rivers Trust, the site is in the Clinton Devon Estates ownership and management. Communications will need to involve the Westcountry Rivers Trust project manager as well as Pebblebed Heaths Manager Kim Strawbridge and Head of Forestry Rob Coventry. Site access will need to be coordinated with Clinton Devon Estates, the landowner, specifically in relation to in-stream work just below Bicton Common due to frequent use by the MOD for endurance training. Health and Safety - The Pebblebed Heaths is open access land with Military of Defence, forestry and conservation operations also occurring. All gates should be opened and closed immediately behind to limit vehicular access. - Access should be discussed with Kim Strawbridge/Rob Coventry of the Pebblebed Heaths Conservation Trust and Clinton Devon Estates - Ground conditions may change and disturbance should be kept to a minimum-do NOT stray other than in the project area. Some of the project area is in protected habitat and designated SSSI. Works must be completed by the 30th September to avoid working in the fish breeding season. Where the Contractor intends to subcontract part of the works, this should be agreed with the Client in advance. The Contractor should ensure that Health & Safety due diligence is carried out and provided to the Client in respect of the Subcontractor either in the form of the WRT Health & Safety Assessment Form or equivalent. As per Condition 21 of the Contract, if the Contractor subcontracts work, it is responsible for Providing the Service as if it had not been subcontracted. Where a Subcontractor is used, The Client reserves the right to instruct the Contractor to stop using a person to Provide the Service. Any disputes are to be resolved in the first instance by the Project Managers of the Client and Contractor. Where a resolution between these two designated individuals is not possible, the dispute should be escalated to the Chief Executives of the parties for resolution. Should the Chief Executives fail to reach agreement the dispute is to be referred to a neutral third party for mediation / conciliation. Only when these steps fail should the dispute be resolved in line with the Contract Data as set out on page 4 of this contract

Scope

5 Requirements for the programme

State whether a programme is required and, if it is, state what form it is to be in, what information is to be shown on it, when it is to be submitted and when it is to be updated. State what the use of the works is intended to be at their Completion as defined in clause 11.2(1).

All works are subject to the conditions of the NE SSSI Consent and DCC Land Drainage Consent as stated below and in the ITT. No deviation is permitted without prior discussion. Works must be completed by the 30th September 2026. Monthly meetings to be held between the client and the contractor.

6 Services and other things provided by the Client

Describe what the Client will provide, such as services (including water and electricity) and ‘‘free issue’’ Plant and Materials and equipment.

| ITEM | DATE BY WHICH IT WILL BE PROVIDED |
| --- | --- |

Site Information

Give information about the site such as the ground conditions and any other information which is likely to affect the Contractor’s work such as the position of adjacent structures.

The site is located on and below the Pebblebed Heaths, Clinton Devon Estate. - Some land is in the East Devon AONB and is in the Pebblebed Heaths SSSI. SSSI consent has been granted and the concept plan must be adhered to. - The landowner is Clinton Devon Estates. - This site has designated status and any concerns or queries should be directed to Milly Bowden and the Pebblebed Heaths manager Kim Strawbridge. - The natural woodland below the heath is used by rangers, forestry, MOD and the general public. - The site has public access, in addition to use under a historic agreement by the Royal Marines as a training ground for recruits. - There are no known water supplies (underground) and electricity (overhead) but site checks should be undertaken by the contractor at each location. - The Royal Marines use an encampment within the common and an endurance course where groups of recruits run around the route across the common. This has caused damage and degradation to the fen, bog, and heath habitats, in addition to exacerbated erosion of peatland soils. A section of the stream which flows straight from Bicton Common is directly above part of the MOD endurance course. This is used frequently. Leaise with project manager and Kim Strawbridge to ensure works will not clash with military training days. Islands Plantation As shown below, the site is located to the west of Yettington. Grid reference SY 04624 85731. WTW gate location for access: ///trading.buzzards.hiring

For further details and photographs of the site, please refer to the Invitation to Tender. For further details and photographs of the site, please refer to the Invitation to Tender.