Contract Data:

Engineering and Construction Short Contract

Engineering and Construction

Short Contract

| A contract between | Westcountry Rivers Trust Rain Charm House, Kyl Kober Parc, Stoke Climsland, Cornwall, PL17 8PH Company Number 06545646 |
| --- | --- |

| and |  |
| --- | --- |

| for | In-stream Natural Flood Management interventions of leaky dams, flow spreaders and woody check dams on Clinton Devon Estate’s Pebblebed Heaths Aylesbeare Common. |
| --- | --- |

Contract Forms

Contract Data

The Contractor’s Offer and Client’s Acceptance

Price List

Scope

Site Information

Notes about the contract are printed in boxes like this one. They are not part of the contract.

Contract Data

The Client’s Contract Data

The Client is

| Name | Westcountry Rivers Trust |
| --- | --- |
| Address for communications | Rain Charm House, Kyl Cober Parc, Stoke Climsland, Cornwall, PL17 8PH |

| Address for electronic communications | millybowden@wrt.org.uk |
| --- | --- |

| The works are | In-stream Natural Flood Management interventions of leaky dams, flow spreaders and woody check dams on Clinton Devon Estate’s Pebblebed Heaths Aylesbeare Common. |
| --- | --- |

| The site is | Aylesbeare Common, Pebblebed Heaths, Clinton Devon Estates |
| --- | --- |

| The starting date is | 1st September 2026 |
| --- | --- |

| The completion date is | 1st December 2026 |
| --- | --- |

| The delay damages are | £50 | per day |
| --- | --- | --- |

| The period for reply is | One | weeks |
| --- | --- | --- |

| The defects date is | Four | weeks after Completion |
| --- | --- | --- |

| The defect correction period is | Eight | weeks |
| --- | --- | --- |

| The assessment day is the | Last Thursday | of each month |
| --- | --- | --- |

| The retention is | 5 | % |
| --- | --- | --- |

The United Kingdom Housing Grants, Construction and Regeneration Act (1996) does/does not apply

(delete as applicable)

The Adjudicator is

| Name | Construction Industry Council (CIC) |
| --- | --- |

| Address for communications | Construction Industry Council (CIC) The Building Centre 26 Store Street London WC1E 7BT |
| --- | --- |

| Address for electronic communications | enquiries@cic.org.uk |
| --- | --- |

Contract Data

The Client’s Contract Data

| The interest rate on late payment is | 0.15 | % per complete week of delay. |
| --- | --- | --- |

Insert a rate only if a rate less than 0.5% per week of delay has been agreed.

| For any one event, the liability |  |
| --- | --- |
| of the Contractor to the Client |  |
| for loss of or damage to the |  |
| Client’s property is limited to | 5,000,000 |

| The Client provides this insurance | None |
| --- | --- |

Only enter details here if the Client is to provide insurance.

| The minimum amount of |  |
| --- | --- |
| cover for the third insurance |  |
| stated in the Insurance Table is, |  |
| for any one event | 5,000,000 |

| The minimum amount of |  |
| --- | --- |
| cover for the fourth insurance |  |
| stated in the Insurance Table |  |
| is, for any one event | 5,000,000 |

| The Adjudicator nominating |  |
| --- | --- |
| body is | Construction Industry Council (CIC) |

| The tribunal is | Arbitration |
| --- | --- |

| If the tribunal is arbitration, the |  |
| --- | --- |
| arbitration procedure is | The latest version of the Institution of Civil Engineers Arbitration Procedure in force when arbitrator is appointed |

The conditions of contract are the NEC4 Engineering and Construction Short Contract June 2017 (with amendments October 2020) and the following additional conditions

Only enter details here if additional conditions are required.

None

Contract Data

The Contractor’s Contract Data

The Contractor is

| Name | To be completed by the contractor |
| --- | --- |
| Address for communications |  |

| Address for electronic communications |  |
| --- | --- |

| The fee percentage is |  | % |
| --- | --- | --- |

The people rates are

| category of person | unit | rate |
| --- | --- | --- |

| The published list of Equipment is |  |
| --- | --- |

| The percentage for adjustment for Equipment is |  | % (state plus |
| --- | --- | --- |
|  |  | or minus) |

The Contractor’s Offer and Client’s Acceptance

The Contractor offers to Provide the Works in accordance with these conditions of contract for an amount to be determined in accordance with these conditions of contract.

| The offered total of the Prices is |  |
| --- | --- |

Enter the total of the Prices from the Price List.

Signed on behalf of the Contractor

| Name |  |
| --- | --- |

| Position |  |
| --- | --- |

| Signature |  |
| --- | --- |

| Date |  |
| --- | --- |

The Client accepts the Contractor’s Offer to Provide the Works

Signed on behalf of the Client

| Name |  |
| --- | --- |

| Position |  |
| --- | --- |

| Signature |  |
| --- | --- |

| Date |  |
| --- | --- |

Price List

Entries in the first four columns in this Price List are made either by the Client or the tenderer. If the Contractor is to be paid an amount for the item which is not adjusted if the quantity of work in the item changes, the tenderer enters the amount in the Price column only; the Unit, Quantity and Rate columns being left blank. If the Contractor is to be paid an amount for the item of work which is the rate for the work multiplied by the quantity completed, the tenderer enters the rate which is then multiplied by the expected quantity to produce the Price, which is also entered.

| ITEM NUMBER | DESCRIPTION | UNIT | QUANTITY | RATE | PRICE |
| --- | --- | --- | --- | --- | --- |

| The total of the Prices | TBC |
| --- | --- |

The method and rules used to compile the Price List are

Scope

The Scope should be a complete and precise statement of the Client’s requirements. If it is incomplete or imprecise there is a risk that the Contractor will interpret it differently from the Client’s intention. Information provided by the Contractor should be listed in the Scope only if the Client is satisfied that it is required, is part of a complete statement of the Client’s requirements and is consistent with the other parts of the Scope.

1 Description of the works

Give a detailed description of what the Contractor is required to do and of any work the Contractor is to design.

Services Required: 1st September – 30th September - Site 1: A cascade of 30 leaky woody dams will be placed in the Back Brook flowing below Five Ponds - Site 2: 25 leaky dams in the northern tributary. 10 Flow spreaders will be placed on overland flow pathways to supplement these in channel dams. 1st September – 1st December - Site 3: 2 goyles to the south of the Back brook channel will have 6 and 10 leaky dams respectively. These channels are eroding and ephemeral. - Site 4: In a large goyle to the south of Harpford Common/Harpford Hill 10 woody check dams will be placed in the channel to slow the ephemeral flow of water and retain some eroding material. - An option of Ground Investigations according to the Consultant’s assessment and agreement with the Client as to whether they are needed. - Appropriate risk assessments will be required for all elements of the services. Under CDM 2015 this includes a Designers Risk Assessment (DRA). - Optioneering for the above outcomes is welcomed against your experience. WRT have provided a Concept Plan (Appendix A), based on technical input, however, WRT are not technical design experts, and while operating as Principal Designer under CDM regulations WRT expect the appointed designer to provide comment on feasibility, health and safety, and budget practicality of options based on your technical experience. - The consultant must ensure that all elements conform to all relevant British and European Standards. Concept Plan Flow spreaders and Leaky dams will slow the movement of water and will increase temporary storage of flood waters within water channels and out on to the floodplain, help delay the passage of flood water downstream, allow sediment to settle out and reduce downstream flood risk. Check dams will restrict flow in the more incised channel in the mire with the aim of wetting up the adjacent peat ground in higher flows. For further details and proposed construction methods, please refer to the Invitation to Tender: In-Stream NFM RSPB Aylesbeare Common.

2 Drawings

List the drawings that apply to the contract.

| DRAWING NUMBER | REVISION | TITLE |
| --- | --- | --- |
| 1 |  | Invitation to Tender: In-Stream NFM RSPB Aylesbeare Common – Appendix A |

Scope

3 Specifications

List the specifications which apply to the contract.

| TITLE | DATE OR REVISION | TICK IF PUBLICLY AVAILABLE |
| --- | --- | --- |
| Invitation to Tender: In-Stream NFM RSPB Aylesbeare Common | 27th May 2026 |  |

4 Constraints on how the Contractor Provides the Works

State any constraints on the sequence and timing of work and on the methods and conduct of work including the requirements for any work by the Client.

All works are subject to NE SSSI Consent and DCC Land Drainage Consent. Consent applications have been submitted and are still pending SSSI approval. Due to the protected status of the SSSI, National Landscape and certain habitats, no additional work, other than discussed here, should be undertaken without prior permission. Once granted, the SSSI and LDC consents can be provided if requested. In rivers that are sensitive to fish spawning, no in-stream work is permitted to be carried out between the dates of 1st October to 31st May (dates inclusive). The main channel of the site has been assessed to have spawning habitat, care must be taken to avoid disturbance of silt and releasing silt into the watercourse. Tributaries and goyle work can be carried out after the end of September. Trees and ground areas with active birds’ nests in MUST be avoided. Note: birds may nest earlier or later than the official nesting season due to local conditions. This work can only commence after the 1st of September. Works must be completed by the 1st December to avoid wet conditions and ground disturbance. Communications While the Client is Westcountry Rivers Trust, the site is owned by Clinton Devon Estates and managed by the RSPB. Communications will need to involve the Westcountry Rivers Trust project manager as well as Pebblebed Heaths Manager Kim Strawbridge and Toby Talylor, RSPB manager. Site access specifically will need to be coordinated with Clinton Devon Estates, the landowner, and Toby Taylor, RSPB manager. Health and Safety - Aylesbeare Common is open access land with forestry and conservation operations also occurring. All gates should be opened and closed immediately behind to limit vehicular access. - Access should be discussed with Toby Taylor, RSPB manager - Ground conditions may change and disturbance should be kept to a minimum-do NOT stray other than in the project area. The tracks are in a protected habitat and designated SSSI. Subcontracting Where the Contractor intends to subcontract part of the works, this should be agreed with the Client in advance. The Contractor should ensure that Health & Safety due diligence is carried out and provided to the Client in respect of the Subcontractor either in the form of the WRT Health & Safety Assessment Form or equivalent. As per Condition 21 of the Contract, if the Contractor subcontracts work, it is responsible for Providing the Service as if it had not been subcontracted. Where a Subcontractor is used, The Client reserves the right to instruct the Contractor to stop using a person to Provide the Service. Dispute resolution Any disputes are to be resolved in the first instance by the Project Managers of the Client and Contractor. Where a resolution between these two designated individuals is not possible, the dispute should be escalated to the Chief Executives of the parties for resolution. Should the Chief Executives fail to reach agreement the dispute is to be referred to a neutral third party for mediation / conciliation. Only when these steps fail should the dispute be resolved in line with the Contract Data as set out on page 4 of this contract For further details and proposed construction methods, please refer to the Invitation to Tender: In-Stream NFM RSPB Aylesbeare Common.

Scope

5 Requirements for the programme

State whether a programme is required and, if it is, state what form it is to be in, what information is to be shown on it, when it is to be submitted and when it is to be updated. State what the use of the works is intended to be at their Completion as defined in clause 11.2(1).

SSSI consent for these works has not yet been granted by Natural England and works are dependent on consent being approved. In rivers that are sensitive to fish spawning, no in-stream work is permitted to be carried out between the dates of 1st October to 31st May (dates inclusive). The main channel of the site has been assessed to have spawning habitat. Tributaries and goyle work can be carried out after the end of September. Trees and ground areas with active birds’ nests in MUST be avoided. Note: birds may nest earlier or later than the official nesting season due to local conditions. This work can only commence after the 1st of September. Works must be completed by the 1st December to avoid wet conditions and ground disturbance. Monthly meetings to be held between the client and the contractor.

6 Services and other things provided by the Client

Describe what the Client will provide, such as services (including water and electricity) and ‘‘free issue’’ Plant and Materials and equipment.

| ITEM | DATE BY WHICH IT WILL BE PROVIDED |
| --- | --- |

Site Information

Give information about the site such as the ground conditions and any other information which is likely to affect the Contractor’s work such as the position of adjacent structures.

Aylesbeare Common – RSPB on behalf of the EA CROC Project As shown on the map below, the site is located to the west of Newton Poppleford. - Aylesbeare Common is located in East Devon within the East Devon Pebblebed Heaths, owned by Clinton Devon Estates and managed by the RSPB. The common is a SSSI - This site has designated status and any concerns or queries should be directed to Milly Bowden and the RSPB manager Toby Taylor. - There are no known water supplies (underground) and electricity (overhead) but site checks should be undertaken at each location by the contractor. - Aylesbeare common is used by RSPB rangers, forestry, and the general public. - The site has public access and conservation grazing.

This tender only concerns the leaky dams and flow spreaders in the map below:

You are welcome to visit the site by arrangement however, it is a large area and not all locations can be guided.  Please let the Project Officer know if you intend to visit the site to prepare your tender response.  A member of WRT staff will organise permission and may accompany you to the site.

For further details, maps, concept plan, construction method and photographs of the site, please refer to the Invitation to Tender: In-Stream NFM RSPB Aylesbeare Common.