













Contract Data:
Engineering and Construction Short Contract






Engineering and Construction



Short Contract
Contract No: 0228



	A contract between
	Westcountry Rivers Trust
Rain Charm House
Kyl Kober Parc
Stoke Climsland
Cornwall PL17 8PH

Company Number 06545646





	and
	TBC







	for
	NFM measures at Hawkerland for the CROC project; Culvert amendment and track repair.





Contract Forms

Contract Data

The Contractor’s Offer and Client’s Acceptance

Price List

Scope

Site Information

	Notes about the contract are printed in boxes like this 
one. They are not part of the contract.





Contract Data

The Client’s Contract Data



The Client is

	Name
	Westcountry Rivers Trust

	
	

	Address for communications
	Rain Charm House, Kyl Cober Parc, Stoke Climsland, Cornwall, PL17 8PH




	Address for electronic communications
	yog@wrt.org.uk / millybowden@wrt.org.uk




	The works are
	NFM measures at Hawkerland for the CROC project; Culvert amendment and track repair.



	The site is
	Hawkerland, Back Brook catchment.  GR SY 05073 88824



	The starting date is
	02/09/2026



	The completion date is
	30/09/2026



	The delay damages are
	£50
	per day





	The period for reply is
	One
	weeks



	The defects date is
	Four
	weeks after Completion



	The defect correction period is
	Four
	weeks



	The assessment day is the
	Last Thursday
	of each month



	The retention is
	5
	%



The United Kingdom Housing Grants, Construction and Regeneration Act (1996) does/does not apply
(delete as applicable)

The Adjudicator is

	Name
	Construction Industry Council (CIC)



	Address for communications
	Construction Industry Council (CIC)
The Building Centre
26 Store Street
London WC1E 7BT




	Address for electronic communications
	enquiries@cic.org.uk









Contract Data

The Client’s Contract Data



	The interest rate on late payment is
	0.15
	% per complete week of delay.



	Insert a rate only if a rate less than 0.5% per week of delay has been agreed.




	For any one event, the liability
	

	of the Contractor to the Client
	

	for loss of or damage to the
	

	Client’s property is limited to
	5,000,000




	The Client provides this insurance
	None



	Only enter details here if the Client is to provide insurance.



	The minimum amount of
	

	cover for the third insurance
	

	stated in the Insurance Table is,
	

	for any one event
	5,000,000



	The minimum amount of
	

	cover for the fourth insurance
	

	stated in the Insurance Table 
	

	is, for any one event
	5,000,000




	The Adjudicator nominating
	

	body is
	Construction Industry Council (CIC)



	The tribunal is
	Arbitration




	If the tribunal is arbitration, the
	

	arbitration procedure is
	The latest version of the Institution of Civil Engineers Arbitration Procedure in force when arbitrator is appointed




The conditions of contract are the NEC4 Engineering and Construction Short Contract June 2017 (with amendments October 2020) and the following additional conditions

	Only enter details here if additional conditions are required.



	None






Contract Data

The Contractor’s Contract Data



The Contractor is

	Name
	TBC

	
	

	Address for communications
	TBC




	Address for electronic communications
	TBC




	The fee percentage is
	 
	%




The people rates are

	category of person
	unit
	rate



	 
	 
	 



	 
	 
	 



	 
	 
	 



	 
	 
	 



	 
	 
	 




	The published list of Equipment is
	 



	The percentage for adjustment for Equipment is
	
	% (state plus

	
	 
	or minus)





The Contractor’s Offer and Client’s Acceptance




The Contractor offers to Provide the Works in accordance with these conditions of contract for an amount to be determined in accordance with these conditions of contract.




	The offered total of the Prices is
	£TBC Excl VAT



	Enter the total of the Prices from the Price List.







Signed on behalf of the Contractor

	Name
	 



	Position
	 



	Signature
	




	Date
	 





The Client accepts the Contractor’s Offer to Provide the Works

Signed on behalf of the Client

	Name
	 



	Position
	 



	Signature
	 



	Date
	 






Price List



	Entries in the first four columns in this Price List are made either by the Client or the tenderer.

If the Contractor is to be paid an amount for the item which is not adjusted if the quantity of work in the item changes, the tenderer enters the amount in the Price column only; the Unit, Quantity and Rate columns being left blank.

If the Contractor is to be paid an amount for the item of work which is the rate for the work multiplied by the quantity completed, the tenderer enters the rate which is then multiplied by the expected quantity to produce the Price, which is also entered.



	ITEM NUMBER
	DESCRIPTION
	UNIT
	QUANTITY
	RATE
	PRICE

	
	
	
	
	
	

	
	
	
	
	
	

	
	
	
	
	
	

	
	
	
	
	
	

	
	
	
	
	
	

	
	
	
	
	
	

	
	
	
	
	
	

	
	
	
	
	
	

	
	
	
	
	
	

	 
	 
	 
	 
	 
	 

	 
	 
	 
	 
	 
	 

	 
	 
	 
	 
	 
	 

	 
	 
	 
	 
	 
	 

	 
	 
	 
	 
	 
	 



	The total of the Prices
	£TBC (Excl VAT)




The method and rules used to compile the Price List are
	 




Scope





	The Scope should be a complete and precise statement of the Client’s requirements. If it is incomplete or imprecise there is a risk that the Contractor will interpret it differently from the Client’s intention.

Information provided by the Contractor should be listed in the Scope only if the Client is satisfied that it is required, is part of a complete statement of the Client’s requirements and is consistent with the other parts of the Scope.




	1 Description of the works



	Give a detailed description of what the Contractor is required to do and of any work the
Contractor is to design.



	Previous/Other relevant NFM works:
In this part of the Back Brook catchment there plans for some conventional NFM works that will be starting on or around delivery of this work (separate contract). These will help control the flow of water down to the culvert and limit sections of the track network, acting like conduits to water flow in high rainfall events.

Services required:
The culvert located approximately at SY 05073 88824, is currently partially blocked and too small to cope with high rainfall events. Work here will remove existing pipe and replace with two pipes to increase flow volume capability. 
Current culvert pipe to be removed and unblocked. 
Additional space created for installation of second pipe, with adequate space between pipes to ensure the gap between them doesn’t become vulnerable to erosion. 
Stone material to be back filled in to culvert area to protect the entrance and pathway under the track.

The damage to the track on lower side of the culvert will be mended using hardcore available on site, plus some additional protection put in at the outfall to protect the northern banks and stabilise the outflow.
Using the hardcore material generated from the excavation required for the second pipe, the current erosion gully which runs perpendicular to the track will be back filled and have suitable topping for trafficking by all vehicles, plus additional robustness to erosion.

Appropriate risk assessments will be required for all elements of the services.  Under CDM 2015 this includes a Designers Risk Assessment (DRA).
Optioneering for the above outcomes is welcomed against your experience.  WRT have provided a Concept Plan (Appendix A), based on technical input, however, WRT are not technical design experts, and while operating as Principal Designer under CDM regulations WRT expect the appointed designer to provide comment on feasibility, health and safety, and budget practicality of options based on your technical experience.
The consultant must ensure that all elements conform to all relevant British and European Standards.

For further detail and information, refer to the ITT: NFM work on Back Brook crossing – Culvert amendment and track repair







	2 Drawings



	List the drawings that apply to the contract.




	DRAWING NUMBER
	REVISION
	TITLE

	1
	
	ITT: NFM work on Back Brook crossing – Culvert amendment and track repair

	
	
	

	 
	 
	 

	 
	 
	 

	 
	 
	 



Scope




	3 Specifications



	List the specifications which apply to the contract.




	TITLE
	DATE OR REVISION
	TICK IF PUBLICLY AVAILABLE

	ITT: NFM work on Back Brook crossing – Culvert amendment and track repair
	August 2026
	 

	 
	 
	 

	 
	
	

	 
	 
	 

	 
	 
	 




	4 Constraints on how the Contractor Provides the Works



	State any constraints on the sequence and timing of work and on the methods and conduct of work including the requirements for any work by the Client.



	Permissions
All works are limited to the actions permitted in the Land Drainage Consent, as detailed in the Scope and in the ITT.  No deviation is permitted without prior discussion. A copy of the Land Drainage Consent can be provided if required.
Communications
While the Client is Westcountry Rivers Trust, the site is at Hawkerland. Communications will need to involve the Westcountry Rivers Trust project manager as well as Clinton Devon Estates. Site access specifically will need to be coordinated with Rob Coventry (CDE Forestry manager), the landowner.

Health and Safety
All visitors to the site should be aware of roaming deer. 

Works must be completed by 30th September.

Where the Contractor intends to subcontract part of the works, the Client should be informed in advance. The Contractor should ensure that Health & Safety due diligence is carried out and provided to the Client in respect of the Subcontractor either in the form of the WRT Health & Safety Assessment Form or equivalent. As per Condition 21 of the Contract, if the Contractor subcontracts work, it is responsible for Providing the Service as if it had not been subcontracted. Where a Subcontractor is used, The Client reserves the right to instruct the Contractor to stop using a person to Provide the Service. 

Any disputes are to be resolved in the first instance by the Project Managers of the Client and Contractor. Where a resolution between these two designated individuals is not possible, the dispute should be escalated to the Chief Executives of the parties for resolution. Should the Chief Executives fail to reach agreement the dispute is to be referred to a neutral third party for mediation / conciliation. Only when these steps fail should the dispute be resolved in line with the Contract Data as set out on page 4 of this contract.




Scope





	5 Requirements for the programme



	State whether a programme is required and, if it is, state what form it is to be in, what information is to be shown on it, when it is to be submitted and when it is to be updated.

State what the use of the works is intended to be at their Completion as defined in clause
11.2(1).




	All works should be completed by 30th September 2026

Interim progress meeting to be held between the client and the contractor mid-September.





	6 Services and other things provided by the Client



	Describe what the Client will provide, such as services (including water and electricity) and ‘‘free issue’’ Plant and Materials and equipment.




	ITEM
	DATE BY WHICH IT WILL BE PROVIDED

	 
	 

	 
	 

	 
	 

	 
	 

	 
	 





Site Information



	Give information about the site such as the ground conditions and any other information which is likely to affect the Contractor’s work such as the position of adjacent structures.



	Hawkerland occupies a great deal of the upper Back Brook catchment.

All visitors to the site should be aware of roaming deer. 
Steep slopes.
Difficult access to individual sites as the vegetation growth is thick in places.
You are welcome to visit the site by arrangement.  Please let the Project Officer know if you intend to visit the site to prepare your tender response.  A member of WRT staff will organise permission and may accompany you to the site

As shown in the map below, the site is located to the West of Newton Poppleford. 
Grid reference SY 05073 88824
Gate location for main access to farm land: ///likening.teaching.person
































For further detail and information, refer to the ITT: NFM work on Back Brook crossing – Culvert amendment and track repair.
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