




















Contract Data:
Professional Service Short Contract



Professional Service



Short Contract
						Contract No:



	A contract between
	Westcountry Rivers Trust
Rain Charm House
Kyl Kober Parc
Stoke Climsland
Cornwall PL17 8PH

Company Number 06545646




	and
	TBC




	for
	Wier removal pre-surveys and design for the River Fal, Cornwall





Contract Forms

Contract Data

The Consultant’s Offer and the Client’s Acceptance

Price List

Scope


	Notes about the contract are printed in boxes like this one. They are not part of the contract.






Contract Data

The Client’s Contract Data




The Client is

	Name
	Westcountry Rivers Trust

	
	

	Address for communications
	Rain Charm House, Kyl Cober Parc, Stoke Climsland, Cornwall, PL17 8PH



	Address for electronic communications
	craig@wrt.org.uk




	The service is
	Wier removal pre-surveys and design for the River Fal, Cornwall



	The starting date is
	28/09/2026



	The completion date is
	30/06/2027



	The delay damages are
	£0
	per day





	The law of the contract is
	The law of England and Wales





	The period for reply is
	One
	weeks



	The defects date is
	Two
	weeks after Completion



	The assessment day is the
	Last Thursday
	of each month




The United Kingdom Housing Grants, Construction and Regeneration Act (1996) does/does not apply
(delete as applicable)
The Adjudicator is
	Name
	Construction Industry Council (CIC)

	
	

	Address for communications
	Construction Industry Council (CIC) 
The Building Centre 
26 Store Street 
London WC1E 7BT



	Address for electronic communications
	enquiries@cic.org.uk









Contract Data

The Client’s Contract Data


	The interest rate on late payment is
	0.15
	% per complete week of delay.



	Insert a rate only if a rate less than 0.5% per week of delay has been agreed.



	The Client provides this insurance
	None



	Only enter details here if the Client is to provide insurance.



The Consultant provides the following insurance cover

	INSURANCE AGAINST
	MINIMUM AMOUNT OF COVER
	PERIOD FOLLOWING COMPLETION OR EARLIER TERMINATION

	Liability of the Consultant for claims made against it arising out of the Consultant’s failure to use the skill and care normally used by professionals providing services similar to the service.
	£5,000,000
	 

	
	in respect of each claim, without limit to the number of claims
	

	Loss of or damage to property and liability for bodily injury to or death of a person (not an employee of the Consultant) arising from or in connection with the Consultant Providing the Service.
	£5,000,000
	 

	
	in respect of each event, without limit to the number of events
	

	Liability for death of or bodily injury to employees of the Consultant arising out of and in the course of their employment in connection with the contract
	£5,000,000
	 

	
	in respect of each event, without limit to the number of events
	



	The Consultant’s total liability to the Client which arises under or in connection with the contract is limited to
	
	

	
	
	

	
	
	£10,000,000



	The Adjudicator nominating body is
	
	

	
	
	Construction Industry Council (CIC)



	The tribunal is
	
	Arbitration



	If the tribunal is arbitration, the arbitration procedure is
	
	The lates version of the Institution of Civil Engineers Arbitration Procedure in force when the arbitrator is appointed.






Contract Data

The Client’s Contract Data



The conditions of contract are the NEC4 Professional Service Short Contract June 2017 (with amendments October 2020) and the following additional conditions

	Only enter details here if additional conditions are required.




	None
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Contract Data

The Consultant’s Contract Data



The Consultant is

	Name
	 



	Address for communications
	 



	Address for electronic communications
	 



	The fee percentage is
	 
	%




The people rates are

category of person	unit 	rate

	 
	 
	 



	 
	 
	 



	 
	 
	 



	 
	 
	 



	 
	 
	 



	If the work is to be carried out on a time change basis the Consultant includes people rates for its own people and people provided by a subcontractor



The key persons are
	
	Name (1)
	 



	
	Job
	 



	
	Responsibilities
	 



	
	Qualifications
	 



	
	Experience
	 



	
	Name (2)
	 



	
	Job
	 



	
	Responsibilities
	 



	
	Qualifications
	 



	
	Experience
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The Consultant’s Offer and Client’s Acceptance





The Consultant offers to Provide the Service in accordance with these conditions of contract for an amount to be determined in accordance with these conditions of contract.


	The offered total of the Prices is
	 




	Enter the total of the Prices from the Price List (Excluding VAT)







Signed on behalf of the Consultant

	Name
	 



	Position
	 



	Signature
	 



	Date
	 





The Client accepts the Consultant’s Offer to Provide the Service

Signed on behalf of the Client

	Name
	 



	Position
	 



	Signature
	 



	Date
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Price List



	The contract does not provide for the Consultant to be paid on a mixture of time charge and Prices and one or the other must be selected.
If the work is to be paid on a time charge basis, only expenses should be included. No other entries should be made in the Price List.
If the Consultant is to be paid on a priced basis the entries in the first four columns are made either by the Client or the tenderer.
For each row:
· If the Consultant is to be paid an amount for the item which is not adjusted if the quantity of work in the item changes, the tenderer enters the amount in the Price column only.
· If the Consultant is to be paid an amount for the item of work and which is the rate for the work multiplied by the quantity completed, the tenderer enters the rate which is then multiplied by the expected quantity to produce the Price, which is also entered. 
Costs incurred by the Consultant other than the listed expenses are included in the Rates and Prices and the People Rates. If expenses are paid at cost, then ‘at cost’ should be entered into the Rate column.
Delete or strike through unused rows.



	ITEM NUMBER
	DESCRIPTION
	UNIT
	EXPECTED QUANTITY
	RATE
	PRICE

	 
	 
	 
	 
	 
	 

	 
	 
	 
	 
	 
	 

	 
	 
	 
	 
	 
	 

	 
	 
	 
	 
	 
	 

	 
	 
	 
	 
	 
	 

	 
	 
	 
	 
	 
	 

	 
	 
	 
	 
	 
	 

	
	

	The total of the Prices
	 

	
	

	EXPENSES

	 
	 
	 
	 
	 
	 

	 
	 
	 
	 
	 
	 

	 
	 
	 
	 
	 
	 





The method and rules used to compile the Price List are
	 




Scope




	The Scope should be a complete and precise statement of the Client’s requirements. If it is incomplete or imprecise, there is a risk that the Consultant will interpret it differently from the Client’s intention. Information provided by the Consultant should be listed in the Scope only if the Client is satisfied that it is required, is part of a complete statement of the Client’s requirements and is consistent with other parts of the Scope.



1 Purpose of the service

	Provide a brief summary of why the service is being commissioned and what it will be used for.



	Through the Open Rivers Programme and the Fal EU Project, Westcountry Rivers Trust (WRT) is seeking to remove three redundant weirs from the River Fal, in order to restore ecological connectivity and open up approximately 35km of river for fish passage along the targeted reach. Further aims associated with this work are the restoration of natural and hydrogeomorphological processes, the reduction of flood risk, and improved habitat heterogeneity.

Services required: Detailed design for the removal of 3 wiers along the river Fal

The consultant is required to complete surveys and detailed designs for the removal of three wiers located along the river Fal, Cornwall including a Pre-Construction Information Pack (PCIP) for construction of the final project. 

The designs will be used to inform contractors of the construction drawings and will provide detailed drawings for use during works, including plans, sections and details as well as a detailed method statement outlining the step-by-step process for each stage of works. They will also be used to support the application process for any required consenting necessary to undertake the final construction. 




2 Description of the service

	Give a complete and precise description of what the Consultant is required to do.



	The consultant is required to complete:

Detailed topographic surveys at each weir to capture the specifications as per Section 3.3(a) of the ITT. The survey must comply with best practice and be supplied in a current AutoCAD format in 2D. The cross-sectional levels information is also required in CSV format. This survey must include enough information for altering any structures, construction of any structures and all statutory permissions including (but not restricted to) Flood Risk Assessment, Environmental Permit, Planning Consent and National Fish Pass Panel approval.

Heritage Impact Assessments (HIA) for each site that meets the standard guidelines of Historic England. The scope of work includes but is not limited to desk based assessment, site survey and visual assessment, significance evaluation, Impact analysis, mitigation recommendations and production of the report. Further detail is included in Section 3.3(b) of the ITT.

Preliminary Ecological Appraisal (PEA) for each site in accordance with CIEEM guidelines for Preliminary Ecological Appraisal, to include as a minimum desk based assessment, extended phase 1 habitat survey, protected species assessment, Recommendations and production of the report. Further detail is included in Section 3.3(c) of the ITT.

(continued on next page)







Scope




	(Description of the service continued from the previous page)

Tree reports including Tree assessment (desk study and site visit) and preparing a report summarizing findings as detailed in Section 3.3(d) if the ITT.

Onsite utilities searches required to understand the location of services which have the potential to be impacted during works. This information will inform project design and RAMS. Further details are included in Section 3.3(e) of the ITT

Ground investigations required to understand the subsurface conditions and structural make-up of each weir. This work will highlight unexpected ground conditions, contamination, sediment levels, flooding, slope instability, or foundation issues which will inform project planning and design options. Further details are included in Section 3.3(f) of the ITT.

Instream sediment analysis required to determine the composition and character of instream materials. This will inform sediment capture or removal techniques to be deployed prior to/during/following proposed works, and the development of a safe system of work to prevent sediment mobilisation and water pollution. Detailed requirements are included in Section 3.3(g) of the ITT

Produce outline designs for each weir, required to establish a preliminary, feasible, and safe plan for decommissioning the structures, providing cost-benefit analysis to inform option selection. Further details are included in Section 3.3(h) of the ITT

The provision of a detailed design (RIBA Stage 4) to ensure weir removals are undertaken safely and in compliance with all legal requirements, and to provide a blueprint for the removal process. The contractor is to supply a comprehensive set of final drawings, specifications, calculations, and construction method statements demonstrating how the weirs will be safely and effectively removed. Further details are included in Section 3.3(i) of the ITT

Additional services (See Section 3.3(j) for details on these) include:
· Production of a Location Plan and Site Plan.
· Flood Risk Assessment.
· Appropriate risk assessments for all elements of the services including a Designers Risk Assessment (DRA). 
· Optioneering for the outcomes against your experience.
· Ensuring the scheme is designed to gain planning approval and any other associated approvals and to be acceptable to statutory and key stakeholders if deemed necessary.
· Monthly updates to the project risk register.

The consultant must ensure that all elements conform to all relevant British and European Standards, and in compliance with the latest edition of:  
· Environment Agency Fish Pass Manual 
· CIRIA River Weirs - Design, maintenance, modification, and removal 
· Civil Engineering Specification for the Water Industry, 7th edition  







Scope



3 Existing information

	List existing information which is relevant to the service. This can include documents which the Consultant is to further develop.



	Full detail of the scope of the work is included in the ITT sent out at the tendering stage. Please refer to this document for detailed information. 



4 Specifications and standards

	List the specifications and standards that apply to the contract.



	The specification and standards are listed in the proposed scope of work. Further information on the works required are also detailed throughout. 

If there are any elements of which the contractor is unsure or needs further clarification this can be clarified with the project manager. 

Please refer to ITT for detailed information




Scope




5 Constraints on how the Consultant Provides the Service


	State any constraints on sequence and timing of work and on method and conduct of work including the requirements for any work by the Client.



	Treviscoe weir lies approx. 10km downstream of the Goss and Tregoss Moors Site of Special Scientific Interest (SSSI) and Special Area of Conservation (SAC) at Goss Moor, and approx. 1.5-2km from St Austell China Clay Pits SAC; any works must have regard to potential impacts on these designated sites and may require Natural England consultation.

The catchment has a long history of tin streaming and china clay extraction; ground and sediment investigations should have regard to the potential for historic mining-related contamination in addition to modern quarrying activity.

Melbur and Treviscoe weirs are located within or adjacent to an active Imerys quarry and therefore, site access requires induction and full PPE at all times (see Section 3.1 of the ITT).

Heritage assets are recorded in the vicinity of all three weirs, including post-medieval leats and former mill/china clay workings (see Section 3.2); any works must be co-ordinated with the Heritage Impact Assessment.

Road and rail infrastructure lies in close proximity to Trenowth weir; any change in impounded water levels must be assessed for impact on these assets.

Japanese knotweed and other invasive non-native species are common along Cornish river corridors; presence/absence should be confirmed through the Preliminary Ecological Appraisal, and biosecurity best practise measures must be adhered to between sites. 

Where the Consultant intends to subcontract part of the works, the Client should be informed in advance.
The Consultant should ensure that Health & Safety due diligence is carried out and provided to the Client
in respect of the Subcontractor either in the form of the WRT Health & Safety Assessment Form or
equivalent. As per Condition 21 of the Contract, if the Consultant subcontracts work, it is responsible for
Providing the Service as if it had not been subcontracted. Where a Subcontractor is used, The Client
reserves the right to instruct the Consultant to stop using a person to Provide the Service.
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Scope





6 Requirements for the programme

	State whether a programme is required and, if it is, state what form it is to be in, what information is to be shown on it, when it is to be submitted and when it is to be updated.



	All proposals should include an estimation of timescales and outline programme of works including
the order and timing of operations to enable the consultant to complete the works by the completion date.





Scope




7 Information and other things provided by the Client

	Describe what information and other things the Client is to provide and by when. Information is that which is not currently available, but will become available during the contract. Other things could include access to a person, place (such as office space or a site) or the Client’s information technology systems.



	ITEM
	DATE BY WHICH IT WILL BE PROVIDED

	Access permission for the completion of the services 
	Upon request. A minimum of 1 weeks notice is required.
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